## Hoja 1
GANTT CHART FOR: "Next Generation Mining ASIC" (16-moth development plan)
Period: January 1st 2026 |  |  |  |  | Highlighted period: | 1 |  |  | Plan duration | [6 empty] | True Start |  |  |  |  | % Filled | [5 empty] | Real (outside the plan) | [7 empty] | % Completed (outside the plan)
ACTIVITY | START | PLAN DURATION | EXPECTED START | EXPECTED DURATION | PERCENTAGE COMPLETED | PERIODOS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80
Hire a recruitment agency | 1 | 3 | 4 | 0 | 0% | bar: PERIODOS 1 to PERIODOS 4
Agency starts and hires team 1 | 4 | 5 | 9 | 0 | 0% | bar: PERIODOS 4 to PERIODOS 9
Agency hires team 2 | 4 | 8 | 12 | 0 | 0% | bar: PERIODOS 4 to PERIODOS 12
Due diligence with the UdeG | 1 | 4 | 5 | 0 | 0% | bar: PERIODOS 1 to PERIODOS 5
Workspace (office) | 1 | 4 | 5 | 0 | 0% | bar: PERIODOS 1 to PERIODOS 5
Basic office equipment acquisition | 2 | 3 | 5 | 0 | 0% | bar: PERIODOS 2 to PERIODOS 5
Workspace Adaptation | 5 | 5 | 10 | 0 | 0% | bar: PERIODOS 5 to PERIODOS 10
Hardware & Work tools acquisition | 1 | 9 | 10 | 0 | 0% | bar: PERIODOS 1 to PERIODOS 10
Basic EDA suite | 4 | 7 | 11 | 0 | 0% | bar: PERIODOS 4 to PERIODOS 11
Advanced EDA Suites (synopsis, siemens) | 11 | 10 | 21 | 0 | 0% | bar: PERIODOS 11 to PERIODOS 21
Arithmetic Core | 0 | 0 | 11 | 24 | 0% | bar: PERIODOS 11 to PERIODOS 34
Conceptualization & Specification | 11 | 2 | 13 | 0 | 0% | bar: PERIODOS 11 to PERIODOS 13
Architecture & Design | 13 | 3 | 16 | 0 | 0% | bar: PERIODOS 13 to PERIODOS 16
RTL design of adder | 16 | 12 | 28 | 0 | 0% | bar: PERIODOS 16 to PERIODOS 28
Logic Syntesis & Optimization | 28 | 7 | 35 | 0 | 0% | bar: PERIODOS 28 to PERIODOS 35
Integration to ASIC Design Standards | 0 | 0 | 35 | 28 | 0% | bar: PERIODOS 35 to PERIODOS 62
Conceptualization & Specification | 35 | 4 | 39 | 0 | 0% | bar: PERIODOS 35 to PERIODOS 39
Architecture & Design | 39 | 4 | 43 | 0 | 0% | bar: PERIODOS 39 to PERIODOS 43
RTL design of adder | 43 | 14 | 57 | 0 | 0% | bar: PERIODOS 43 to PERIODOS 57
Logic Syntesis & Optimization | 57 | 6 | 63 | 0 | 0% | bar: PERIODOS 57 to PERIODOS 63
Integration to ASIC Manufacturing Standards | 0 | 0 | 63 | 12 | 0% | bar: PERIODOS 63 to PERIODOS 74
Floor planning | 63 | 4 | 67 | 0 | 0% | bar: PERIODOS 63 to PERIODOS 67
Placement | 67 | 4 | 71 | 0 | 0% | bar: PERIODOS 67 to PERIODOS 71
Routing | 71 | 4 | 75 | 0 | 0% | bar: PERIODOS 71 to PERIODOS 74